## Sheet1
Tasks	Estimated time (DD/MM/YY)	Actual time (DD/MM/YY)

Finishing module exercises	-	19/09/23
Preparations/placeholder data	-	19/09/23
Documentation template filling	20/09/23 – Before 2 p.m	20/09/23 – 3 p.m
Lo-Fi designs on FIGMA	21/09/23 – Before 2 p.m	20/09/23 – day end
Basic page design	21/09/23 – Before day end	21/09/23 – day end
CRUD basic operations	23/09/23 – Before 4 p.m	23/09/23 – 4 p.m
Basic UI improvements (Themes)	24/09/23 – Before day end	25/09/23 – 4 p.m
Login and user details page creation	25/09/23 – Before noon	25/09/23 – 4 p.m
Individual project page display	25/09/23 – Before 4 p.m
User fields choice	25/09/23 – Before day end
CRUD other operations	26/09/23 – Before 4 p.m
Breakpoint – documentation of previous files and results	26/09/23 – Before day end	26/09/23 –Day end
Adding theming options and improving UI – add responsiveness	27/09/23 – Before 2 p.m
Adding cookies for user and theme saving	27/09/23 – Before day end
Adding resources to steps and budgets to projects	28/09/23 – Before day end
Breakpoint – documentation of previous files and results	29/09/23 – Before day end
Polishing UI / Choosing what is displayed on which media	01/10/23 – Before day end
Actions building with AWS	02/10/23 – Before day end
Adding email verification	03/10/23 – Before day end	Dropped
Breakpoint – documentation of previous files and results	04/10/23 – Before 2 p.m
Adding payment to increase project budget	05/10/23 – Before 2 p.m
End of documentation, preparation of slides and time margin	06/10/23 – Before day end